## Sheet1
Sr.No | Type | Task Title | Assignees | Status | Commented By | Comment | Date
1 | Issue | Riddhi - TIR Prod SAP Auto Export Status | Vrushali-gohel, RiddhiBaraiya | open | Vrushali-gohel | <img width="1366" height="768" alt="Image" src="https://github.com/user-attachments/assets/25dd218c-6e8a-4b4c-8338-7b1dd88356f3" /> | 2025-07-30
2 | Issue | Deep | ShahDeep5113 | open | ShahDeep5113 | 1. Works on IPCL Report (Shell Breakage Report) In Database. 2. Create SPs for this report and updating templates. 3. GET Employee Master Table and used in the SBR. 4. testing Done for Shell Breakage | 2025-07-30
3 | Issue | HONDA : TR : SR94291 For YES/No and Date Validate | Vishal-Bhaliya | open | Vishal-Bhaliya | <img width="903" height="587" alt="Image" src="https://github.com/user-attachments/assets/d1a6e77f-8d7a-4aad-838f-0aae1df7028c" /> | 2025-07-30
4 | Issue | HONDA : TR :- Batch/Employee Option | ShahDeep5113, Vishal-Bhaliya | open | Vishal-Bhaliya | <img width="903" height="587" alt="Image" src="https://github.com/user-attachments/assets/863c314e-4191-4561-9c97-c0a6995e11a5" /> | 2025-07-30
5 | Issue | NP1141-INC-450913-add edit rights in SCR database for DTC team | Nandini-RI | closed | Nandini-RI | Assign all three people to "Editor" role. Asked to user for verify. | 2025-07-30
6 | Issue | Kontoor: Sarge - Re: SARGE ISSUE | Unassigned | open | Vrushali-gohel | - Reset user account<M.Elghobary@lotusgarments.com> password in sarge production | 2025-07-30
7 | Issue | Kontoor: SCR0217 - InfoCenter CoC: Edit function amendment [] | Kinjal-Makwana, Ravi-Morichauhan | open | Vrushali-gohel | - Apply logic to edit maker data and test. | 2025-07-30
8 | Issue | Vrushali | Vrushali-gohel | open | Vrushali-gohel | - https://github.com/RI-BVN/RamansheeRepo/issues/230 -- Checked log - https://github.com/RI-BVN/RamansheeRepo/issues/633 -- reset account password - https://github.com/RI-BVN/RamansheeRepo/issues/450 | 2025-07-30
9 | Issue | Miloni | Miloni-Mehta04 | open | Miloni-Mehta04 | Working on UI for VMI CRS Account Function and some modification in it | 2025-07-30
10 | Issue | Ravi | Ravi-Morichauhan | open | Ravi-Morichauhan | 1. RoofTopLight Company Stock List – Ensure proper filtering, pagination, and design. 2. RoofTopLight ConfirmOrder - proper filtering, pagination, and design. 3. RoofTopLight Challan List - proper fil | 2025-07-30
11 | Issue | Utsav | Utsav-Patel9 | open | Utsav-Patel9 | Powerapp : 1. Daily Stock Adjustment List in second screen in add field 2. Daily Stock Adjustment List in design complete 3. Daily Stock Adjustment List in click on edit and all screen value bind scre | 2025-07-30
12 | Issue | Rakesh | Rakesh-Morichauhan | open | Rakesh-Morichauhan | 1. Add/Update (Alert Massage in Insert successfully completed Or Update Successfully Completed) 2. Insert Data Receipt Upload (Optional) jpg, png, etc. 3. Department Head List page and Edit models | 2025-07-30
13 | Issue | HONDA : SR101180 :Travel billing module | ShahDeep5113, Vishal-Bhaliya, Urmi-Parmar | open | Vishal-Bhaliya | <img width="800" height="458" alt="Image" src="https://github.com/user-attachments/assets/16cf95b2-3d43-4377-8cf6-0d67a4c3fb0f" /> | 2025-07-30
14 | Issue | Kinjal | Kinjal-Makwana | open | Kinjal-Makwana | **In 1st Half** - Ticket, Outstanding file update - #617 - Replied user - #590 - Replied user - #618 - Replied user - Weekly meeting from 1 to 2 **In 2nd Half** - #630 - Work and replied user | 2025-07-30