## Sheet1
Sr.No | Type | Task Title | Assignees | Status | Commented By | Comment | Date
1 | Issue | Kinjal | Kinjal-Makwana | open | Kinjal-Makwana | **In 1st Half** - Ticket, Outstanding file update - #617 - Replied user - #590 - Replied user - #618 - Replied user - Weekly meeting from 1 to 2 **In 2nd Half** - #630 - Work and replied user - https | 2025-07-30
2 | Issue | Riddhi - TIR Prod SAP Auto Export Status | Vrushali-gohel, RiddhiBaraiya | open | Vrushali-gohel | <img width="1218" height="560" alt="Image" src="https://github.com/user-attachments/assets/daedf98b-d8ac-4c6e-984f-f702cd561b79" /> | 2025-07-31
3 | Issue | HONDA : SR102099 -Emp.Code-12782-Rellocation click forgated | Vishal-Bhaliya | open | Vishal-Bhaliya | <img width="900" height="757" alt="Image" src="https://github.com/user-attachments/assets/2afa467f-943d-45a1-97ad-87fc1694243b" /> | 2025-07-31
4 | Issue | HONDA : PR dashboard access - SR99647 | Urmi-Parmar | open | Vishal-Bhaliya | change log shared with <img width="800" height="458" alt="Image" src="https://github.com/user-attachments/assets/7a420465-48f4-4980-838e-4da8ed0cd776" /> | 2025-07-31
5 | Issue | HONDA : SR100081 : Roaster Extra Seat add For Div based on OP seat margin | ShahDeep5113, Vishal-Bhaliya | open | Vishal-Bhaliya | Need To correct Some Functionality after discussion with satyaveer san aS ON 30-07-205 | 2025-07-31
6 | Issue | HONDA : SR104589 - SHE Documents on Employee portal | Vishal-Bhaliya | closed | Vishal-Bhaliya | Go live on 30-07-2025 3:30 PM | 2025-07-31
7 | Issue | Kontoor: Sarge - Re: Test Requests [TR202507024338 & TR202507024340] Submitted to Applicant (Unlock User<alauddin@sharmingroup.com>) [INC-451203] | Unassigned | open | Vrushali-gohel | - Unlock user account<alauddin@sharmingroup.com> in sarge production | 2025-07-31
8 | Issue | Deep | ShahDeep5113 | open | ShahDeep5113 | 1. Working on Honda : SR100081. 2. add two new field in the table and add also in the edmx in the Eportal. | 2025-07-31
9 | Issue | KT Session of Kontoor | Kinjal-Makwana | open | Kinjal-Makwana | Date: 29-07-2025 **Continue for Infocenter** - Sample Evaluation Menu - Merchandiser, QA - Sample Evaluation Menu - Discussion on issue received from Merchandiser | 2025-07-31
10 | Issue | KT Session of Kontoor | Kinjal-Makwana | open | Kinjal-Makwana | Date: 30-07-2025 - Start to Prepare document for Infocenter | 2025-07-31
11 | Issue | Kontoor: SCR0217 - InfoCenter CoC: Edit function amendment [] | Kinjal-Makwana, Ravi-Morichauhan | open | Vrushali-gohel | - Modify UI and Add edit logic COC_MakerAdd and COC_MakerEdit and test - Update data of qalr_vendor vendor_name (replace enter key and tab) | 2025-07-31
12 | Issue | Vrushali | Vrushali-gohel | open | Vrushali-gohel | - https://github.com/RI-BVN/RamansheeRepo/issues/230 -- Checked Log - https://github.com/RI-BVN/RamansheeRepo/issues/639 -- Unlock sarge user in production - https://github.com/RI-BVN/RamansheeRepo/is | 2025-07-31
13 | Issue | Rakesh | Rakesh-Morichauhan | open | Rakesh-Morichauhan | 1. Update Get By formDate or Todate And Get By ReqUpload Show in Edit Models. 2. TourRequest Project approve,rejected,sendback with department. 3. TourRequest Project approve,rejected,sendback with F | 2025-07-31
14 | Issue | KT Session of Kontoor | Kinjal-Makwana | open | Kinjal-Makwana | **Continue for Infocenter** - Washing/ Color Evaluation -> Bulk Fabric/ Lab Dip -> Prepare Request -Discussion on issue received for this - Washing/ Color Evaluation -> Bulk Fabric/ Lab Dip -> Prepare | 2025-07-31
15 | Issue | Utsav | Utsav-Patel9 | open | Utsav-Patel9 | Powerapp : 1. Daily Stock Adjustment List in second screen in add dropdown 2. FTIC_QRCode_Generator in QrCode design changes process 144 MODEST: 3. Fill the Database backup file in excel | 2025-07-31
16 | Issue | Kinjal | Kinjal-Makwana | open | Kinjal-Makwana | **In 1st Half** - #629 - Check and replied user - #628 - Check and replied user - https://github.com/RI-BVN/RamansheeRepo/issues/450- Call with Vicky - Ticket, Outstanding file update **In 2nd Half** | 2025-07-31
17 | Issue | Miloni | Miloni-Mehta04 | open | Miloni-Mehta04 | Exploring OpenID and Response Cache in .net Core Updating Excel Document for the object reference used to move from development to production Flowchart document for the Flow Init Process | 2025-07-31