## Sheet1
Sr.No | Type | Task Title | Assignees | Status | Commented By | Comment | Date
1 | Issue | Riddhi - TIR Prod SAP Auto Export Status | Vrushali-gohel, RiddhiBaraiya | open | Vrushali-gohel | <img width="1185" height="551" alt="Image" src="https://github.com/user-attachments/assets/7b049362-d70a-4012-a1ce-a071de56c359" /> | 2025-08-19
2 | Issue | Kontoor: P01858: TIR APAC error - shipment AWB [INC-455192] | Unassigned | open | Vrushali-gohel | 14 Aug - Update procedure to prevent data like &amp;amp.... in production and devloment - check for SHIPMETAWB_UPDATE Data | 2025-08-19
3 | Issue | TIR APAC - Import Historical Data | Kinjal-Makwana, Vrushali-gohel | open | Vrushali-gohel | 14 Aug - Update data for Unitprice(Other) and import in smart-sheet. 18 Aug - Replay in mail for priceunit data in smartsheet | 2025-08-19
4 | Issue | Kontoor: Sarge - Re: unlock my SARGE account | Unassigned | open | Vrushali-gohel | 18 Aug - Unlock Sarge user in production | 2025-08-19
5 | Issue | Kontoor: Sarge - Re: KB/RADISSON CASUAL WEAR/WESTERN B I&T/BABY BOYS /STYLE: 10PQJ136D/NEED SUPPLIER DETAILS | Unassigned | open | Vrushali-gohel | 18 Aug - Re-active sarge user in production | 2025-08-19
6 | Issue | Kontoor: Sarge - VF / Kontoor Brands Password Reset Kontoor Update | Unassigned | open | Vrushali-gohel | 18 Aug - Unlock sarge User in production | 2025-08-19
7 | Issue | Kontoor: Sarge - Re: System locked | Unassigned | open | Vrushali-gohel | 18 Aug - Unlock sarge account in prodution | 2025-08-19
8 | Issue | Kontoor: Sarge - Re: Sarge extract for testing data comparison | Unassigned | open | Vrushali-gohel | 18 Aug - Create new user account with sourcing role in production | 2025-08-19
9 | Issue | Vrushali | Vrushali-gohel | open | Vrushali-gohel | 14 Aug - https://github.com/RI-BVN/RamansheeRepo/issues/230 -- Checked log - https://github.com/RI-BVN/RamansheeRepo/issues/13 -- Update priceunit data and import in smartsheet - https://github.com/R | 2025-08-19
10 | Issue | Ravi | Ravi-Morichauhan | open | Ravi-Morichauhan | Date : 14-08-2025 1. BMC project with Mihir Bhai change in Master table | 2025-08-19
11 | Issue | Kontoor: Sarge - RE: Lee Slam Jim - Nihon Menpu #KR-77510-WH10ST | Unassigned | open | Vrushali-gohel | - Create new sarge account with supplier role in production - Create new supplier in production | 2025-08-19
12 | Issue | Kontoor: SCR0185: Shipment’s RFQ process | Kinjal-Makwana, Vrushali-gohel | open | Vrushali-gohel | 1. Set shipper as drop down list when Logistics team login (raise request on behalf of external users) : NGC request: add shipper Dropdown list - Vendor List -- In Process (Only mail logic) Non | 2025-08-19
13 | Issue | Vrushali | Vrushali-gohel | open | Vrushali-gohel | - https://github.com/RI-BVN/RamansheeRepo/issues/230 -- Checked Log - Check with nandini mam for SCR DB - https://github.com/RI-BVN/RamansheeRepo/issues/153 -- Worked as listed in the task - https:// | 2025-08-19
14 | Issue | SCOFP: Flow Init Upload Files to Upload | Miloni-Mehta04 | open | Miloni-Mehta04 | Implementing validating Duplicate Logic in Flow Init Files To Upload Testing Duplication Test Cases | 2025-08-19
15 | Issue | Miloni | Miloni-Mehta04 | open | Miloni-Mehta04 | Implementing validating Duplicate Logic in Flow Init Files To Upload Work with Kinjal Ma'am to understand how to create KIM user request in Info center | 2025-08-19
16 | Issue | Kinjal | Kinjal-Makwana | open | Kinjal-Makwana | **In 1st Half** - https://github.com/RI-BVN/RamansheeRepo/issues/153 - Prepare working for Case 46 and explain changes for NonNGC to Vrushali - Ticket, Outstanding file update - #703 - Check and repli | 2025-08-19
17 | Issue | HONDA : SR101107 - Pending batch in TR | Vishal-Bhaliya | closed | Vishal-Bhaliya | Go Live as on 19-08-2025 | 2025-08-19
18 | Issue | HONDA : Discussion on Mapping of Fixed Asset Register in Asset Transfer Process. | Vishal-Bhaliya | closed | Vishal-Bhaliya | close in accordance with Rishabh San's communication with the SAP team and uSer | 2025-08-19
19 | Issue | HONDA : 220210-tour settlement issue | Unassigned | closed | Vishal-Bhaliya | close | 2025-08-19